## Bug Log
Iteration | Feature | Bug Features | Impact | Found By | Date Found | Resolved On | Occurrence | total
3 | Login | Typo for retrieveUsernameFromEmail() method | Low (1) | Yigang | 2017-10-01 | 2017-10-03 | 1 | 1
3 | Login | Unable to login with correct username and password | High (5) | Yigang | 2017-10-01 | 2017-10-03 | 1 | 5
3 | Login | Admin gets stuck at a blank authenticate.jsp | Critical (10) | Samantha | 2017-10-01 | 2017-10-03 | 1 | 10
3 | Bootstrap | Unable to create folder when deployed to AWS | High (5) | Amos | 2017-10-05 | 2017-10-06 | 1 | 5
4 | Auto Group Detection Top K Companions Top K Next Places | Dropdown for user logout not working | Low (1) | Rainean | 2017-10-12 | 2017-10-15 | 3 | 3
4 | Top K Companions Top K Next Places | Submit button missing | High (5) | Rainean | 2017-10-12 | 2017-10-15 | 2 | 10
4 | Top K Companions Top K Next Places | Gets stuck at the controller page | Critical (10) | Yigang | 2017-10-12 | 2017-10-15 | 2 | 20
4 | Top K Next Places | Does not show ties in rank | Low (1) | Xinyi | 2017-10-12 | 2017-10-15 | 1 | 1
5 | Top K Popular Places | Input time of 12:00:00 gets converted into 00:00:00 | High (5) | Amos | 2017-10-19 | 2017-10-19 | 1 | 5
5 | Top K Popular Places | Ranking does not show all | High (5) | Amos | 2017-10-19 | 2017-10-19 | 1 | 5
5 | Top K Popular Places | If input date time does not have data, page gets stuck at controller | Critical (10) | Yigang | 2017-10-19 | 2017-10-19 | 1 | 10
5 | Heatmap | Considers location updates outside the 15 min query window | High (5) | Samantha | 2017-10-19 | 2017-10-19 | 1 | 5
5 | Heatmap | Results don’t show density 0 | Low (1) | Samantha | 2017-10-19 | 2017-10-19 | 1 | 1
5 | Bootstrap | lowercase gender was not added in | Low (1) | Rainean | 2017-10-22 | 2017-10-23 | 1 | 1
5 | Bootstrap | Wrong email was added in | Low (1) | Rainean | 2017-10-22 | 2017-10-23 | 1 | 1
5 | Boostrap | Less than 8 characters still goes in for password | Low (1) | Rainean | 2017-10-22 | 2017-10-23 | 1 | 1
5 | Boostrap | Error message for blank fields is not shown | Low(1) | Rainean | 2017-10-22 | 2017-10-23 | 3 | 3
5 | BootstrapController | filePart.getContentType().equals("application/octet-stream") results in system processing bootstrap despite no zip file being selected. This results in a "Cannot call sendRedirect() after the response has been committed" error | Low (1) | Amos | 2017-10-22 | 2017-10-23 | 1 | 1
5 | HeatmapController | Clicking on invalid date range (2010-02-06 10:00:17) returns semantic places with values all to zero instead of no data found. | High (5) | Rainean | 2017-10-22 | 2017-10-23 | 1 | 5
5 | Breakdown | Results return the wrong count | High (5) | Amos | 2017-10-22 | 2017-10-23 | 1 | 5
5 | Auto Group Detection | No output/results because list returned in the while loop does not contain elements even though it should have | Critical (10) | Amos | 2017-10-22 | 2017-10-23 | 1 | 10
5 | Top K Companions | No data makes page stuck at the controller | Critical (10) | Rainean | 2017-10-22 | 2017-10-23 | 1 | 10
5 | Top K Companions | With data makes page stuck at the controller because it stops processing at the for loop for calculating together time | Critical (10) | Amos | 2017-10-22 | 2017-10-23 | 1 | 10
5 | Top K Companions | Stuck at controller page for any input | Critical (10) | Yigang | 2017-10-24 | 2017-10-24 | 5 | 50
5 | Bootstrap | Email doesn't catch emails without a period separator between name and year. eg " deshaun.jackson2016@economics.smu.edu.sg" | Low (1) | Rainean | 2017-10-29 | 2017-10-31 | 1 | 1
6 | Top K Next Places | not handling case when there is no data found | High (5) | Samantha | 2017-11-01 | 2017-11-02 | 1 | 5
6 | Bootstrap | Not showing error messages properly | Low (1) | Yigang | 2017-10-31 | 2017-10-31 | 12 | 12
6 | Bootstrap (Additional) | All rows did not go in if there is a duplicate | High (5) | Yigang | 2017-10-31 | 2017-10-31 | 1 | 5
6 | Breakdown | exception report/ null pointer error (happens when i enter any category for default date value. probably not handling when no data found for that date?) | High (5) | Samantha | 2017-11-02 | 2017-11-02 | 1 | 5
6 | Top K Companions | test case4(no companion found): change test data time to 2017-02-06 16:00:01 | High (5) | Samantha | 2017-11-02 | 2017-11-02 | 1 | 5
6 | Top K Companions | test case6(same semantic place different loc id): change test data time to 2017-02-07 20:30:00 add "no companion found" in expected result | High (5) | Rainean | 2017-11-02 | 2017-11-02 | 1 | 5
6 | Top K Next Places | test case2(no location updates found): change test data time to 2014-02-06 16:00:01 | High (5) | Rainean | 2017-11-02 | 2017-11-02 | 1 | 5
6 | Heatmap | Page displays error when date: 2017-02-32T12:45:00 or when floor is invalid when submitting json request (class cast exception) | High (5) | Yigang | 2017-11-03 | 2017-11-03 | 1 | 5
6 | Top K Next Places | Page displays error when only [localhost:8084/app/json/top-k-next-places] is sent (NPE) | High (5) | Yigang | 2017-11-03 | 2017-11-03 | 1 | 5
6 | Top K Next Places DAO | JSON and UI submission results in error with origin: SMUSISL1WAITINGAREA date: 2017-02-06T12:45:00 token: valid bootstrap: NextPlaceCompanionData | High (5) | Yigang | 2017-11-03 | 2017-11-03 | 1 | 5
6 | Top K Companions | JSON submission results in error with mac address: all results in invalid mac address when there is suppose to be a result, 90a3382bab4744edc475fea1700c7032343994b3 | High (5) | Samantha | 2017-11-03 | 2017-11-03 | 1 | 5
6 | Top K Companions | Test case 1 codes show 252 but in data is 180 of tgttime For MAC add: 30a3382bab4744edc475fea1700c7032343994b3 | High (5) | Yigang | 2017-11-03 | 2017-11-03 | 1 | 5
6 | JSON | If token is invalid, it still goes through as valid | High (5) | Rainean | 2017-11-07 | 2017-11-18 | 1 | 5
6 | Bootstrap | Password is not validated correctly | Critical (10) | Yigang | 2017-11-09 | 2017-11-16 | 1 | 10
6 | Heatmap | Heatmap graphical cant be read, it doesn’t work. | High (5) | Xinyi | 2017-11-09 | 2017-11-18 | 1 | 5
6 | Breakdown | breakdown percentage is wrong | High (5) | Xinyi | 2017-11-09 | 2017-11-16 | 1 | 5
6 | Breakdown | combine same ranks or colour code if its in different rows | Low (1) | Xinyi | 2017-11-09 | 2017-11-16 | 1 | 1
6 | Top K Companions | Show email for top k companions only for test 13 because test 14 works. Check why this is the case | Critical (10) | Xinyi | 2017-11-09 | 2017-11-16 | 1 | 10
6 | Auto Group Detection | Email should be shown for agd for 18 but 19 only one didn’t come up | Critical (10) | Xinyi | 2017-11-09 | 2017-11-16 | 1 | 10
6 | Bootstrap | location csv does not check for invalid timestamp | Critical (10) | Amos | 2017-11-09 | 2017-11-16 | 1 | 10
6 | Top K Companions | Emails of some companions are not shown | High (5) | Amos | 2017-11-09 | 2017-11-16 | 1 | 5
7 | Bootstrap | HTTP STATUS 405 | Critical (10) | Rainean | 2017-11-17 | 2017-11-18 | 1 | 10
7 | Bootstrap | for demographics.csv, it shows invalid gender first, then invalid password | High (5) | Rainean | 2017-11-17 | 2017-11-18 | 1 | 5
7 | Bootsrap | when there is an error for location id (invalid location: location id does not exist in the locationlookup.csv), while also having invalid timestamp and/or invalid mac address, the error for invalid location does not appear | High (5) | Samantha | 2017-11-18 | 2017-11-18 | 1 | 5
7 | Boostrap | Over-validation for location-id. does not have to be length of 10 | Critical (10) | Samantha | 2017-11-18 | 2017-11-18 | 1 | 10
7 | Bootstrap | For demographics, bootstrap doesn’t show correct error message | High (5) | Samantha | 2017-11-18 | 2017-11-18 | 1 | 5
7 | Top K Next Place | Location: JSON - next places Impact: High returns null pointer error when parameters are blank/missing | Critical (10) | Xinyi | 2017-11-18 | 2017-11-19 | 1 | 10
Note on G1: Amos Lee: [Resolved On] column added in after Iteration 5, In Class Demo

## Bug Metric
Duration | Iteration | Score | Action
Week 6 - Week 7 (25/9 - 8/10) | 3 | 21 | Prioritize bugs to be fixed during next PP session.
week 8 (9/10 - 15/10) | 4 | 34 | Bugs found at the end of current iteration. Since the score only reached more than 10 on the last day of the iteration, we couldn't adjust the current iteration anymore. Thus, we added debugging sessions in the next iteration.
Week 9 - Week 10 (16/10- 29/10) | 5 | 63 | PM reschedules project with debugging sessions as priority before continuing with the current iteration.
Week 11 - Week 12 (30/10 - 12/11) | 6 | 63 | PM reschedules project with debugging sessions as priority before continuing with the current iteration.
Week 13 - week 14 (12/11 - 23/11) | 7