## Slide 1: Software Engineering Final Presentation Team XRAYS (G7T9)

## Slide 2: Table of contents
Schedule
Improvement
Breakdown on Work
Task and Bug Metrics
Use of GIT
Test Score
Server Info
Others
The agenda for today

## Slide 3: 1. SCHEDULE
To code or not to code

## Slide 4: Actual vs Planned
Chart: Burndown
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Planned | 353.75 | 343.75 | 333.75 | 286.75 | 199.75 | 95.5 | 45.5 | 0
Actual | 353.75 | 339.75 | 325.75 | 279.25 | 218 | 121.1667 | 52.9167 | 7.4167
# | Planned | Actual
0 | 354 | 354
1 | 344 | 340
2 | 334 | 326
3 | 287 | 279
4 | 200 | 218
5 | 96 | 121
6 | 46 | 53
7 | 0 | 7

## Slide 5: Planned
Basic Location Report
Heatmap
In Class Demo
Auto Group Detection
Update Sequence Diagram
Auto Group Detection
Deployment
UAT
5 x Debugging
5 | 6 | 7
4 x Debugging
2 x Integration Testing
2 x Regression Testing
Final Presentation Preparation

## Slide 6: Actual
4 x Debugging
2 x Integration Testing
2 x Regression Testing
Final Presentation Preparation
5 | 6 | 7
Basic Location Report
Heatmap
In Class Demo
4 x Auto Group Detection
1 x Update Sequence Diagram
Auto Group Detection
Deployment
UAT
5 x Debugging
+ 2 x Debugging

## Slide 7: Functionalities
Implemented Functionalities | Login & Logout Bootstrap & Additional Data Upload Heatmap Basic Location Report - Top K Popular Places Basic Location Report – Breakdown Basic Location Report – Top K Companions Basic Location Report – Top K Next Place Auto Group Detection
Add On Functionalities | Dashboard (Allow admin to truncate each single database table)

## Slide 8: Frameworks/ External Libraries
Frontend Framework:
Bootstrap
SB Admin 2
Frameworks Used:
Model View Controller
(JSP Model 2)
Frontend Library
jQuery
metisMenu
Backend Libraries:
MySQL JDBC Driver
gson-2.8.2.jar
is203-jwt-v2.jar
json-smart-1.2.jar
nimbus-jose-jwt-2.26.1.jar
opencsv-4.1.jar

## Slide 9: Challenges Faced
Project Manager/Leader
Being new to both the Software Engineering process and taking on the role of a project manager, there were many uncertainties and differing viewpoints. Many times the leader is just as lost as the other members but as the project manager, the leader has to come up with a game plan albeit having little to no experience and banking on a whole lot of Google and EvaLive. Given that there is no sample/model answer, we often sought other groups as point of reference and also comfort in knowing that we are on the right track.
More often than not, the programmers are waddling neck deep in codes and tend to forget to update the schedule. Therefore the Project Manager has to constantly remind the programming teams to update the schedule with the commit ID and the pair programming photos (which we didn’t realise wasn’t a requirement until Week 13). In order to ensure that the Project Manager is kept abreast of the pair programming teams’ schedule, the aid of Google Calendar was enlisted which proved to be a much needed and necessary companion in this quest to ensure that the project schedule is up to date.

## Slide 10: 2. IMPROVEMENT
Improvement begins with I

## Slide 11: Comments We Received
Plain UI
Unbalanced Hours

## Slide 12: What We Did
Added a [Resolved On] column in bug logs for better accountability
Project Managers took a more active role by checking in with Pair Programmers
Spending more time and effort during project kickstart to iron out any possible planning issues
Plain UI
Unbalanced Hours
Added in preloading screen when awaiting results
PM did better job allocations this time
 | Xinyi | Rainean | Amos | Yigang | Samantha
Prog Hrs | 71 | 67 | 74 | 71 | 67
Non-prog Hrs | 105 | 108 | 105 | 114 | 113

## Slide 13: 3. BREAKDOWN OF WORK
Lets get down to business

## Slide 14: Overall Work Breakdown
Chart: 
| Xinyi | Rainean | Amos | Yigang | Samantha
Programming Hours | 71 | 67 | 74 | 71 | 67
Chart: Non-Programming Hours
| Xinyi | Rainean | Amos | Yigang | Samantha
Programming Hours | 105 | 108 | 105 | 114 | 113
Chart: Hours Per Member
| Xinyi | Rainean | Amos | Yigang | Samantha
Programming | 71 | 67 | 74 | 71 | 67
Non-Programming | 105 | 108 | 105 | 114 | 113

## Slide 15: Member: Xinyi
Programming (71 Hours) | Non-Programming (105 Hours)
Bootstrap (Import & Validation) Basic Location Reports (Breakdown, Top K Companions, Top K Next Places, Top K Popular Place) System Integration Debugging | Review system design Review technical documents Preparation for Milestones (PM Review, Online Demo) Testing (Unit, System Integration, Regression) AWS Deployment
Chart: 
Chart: 
| Programming | Non-Programming
Work Breakdown | 71 | 105

## Slide 16: Member: Rainean
Programming (67 Hours) | Non-Programming (108 Hours)
Login Page Bootstrap (Import) Basic Location Reports (Breakdown, Top K Companions, Top K Next Places, Top K Popular Place) Integration (Top K Companions, Top K Next Places, AGD) Debugging | Review system design Review technical documents Preparation for Milestones (PM Review, Online Demo) Testing (Unit, System Integration) AWS Deployment
Chart: 
| Programming | Non-Programming
Work Breakdown | 67 | 108

## Slide 17: Member: Amos
Programming (74 Hours) | Non-Programming (105 Hours)
Bootstrap (Import, Validate, Logic) Login Page Basic Location Reports (Breakdown, Top K Popular Place) AGD Heatmap Debugging | Review system design Review technical documents Preparation for Milestones (PM Review, Online Demo) System Integration & Regression Testing AWS Deployment Testing (Unit, System Integration)
Chart: 
| Programming | Non-Programming
Work Breakdown | 74 | 105

## Slide 18: Member: Yigang
Programming (71 Hours) | Non-Programming (114 Hours)
Login Page Bootstrap (Import, Validate) Basic Location Reports (Top K Next Places, Breakdown, Top K Popular Place) Debugging | Review system design Review technical documents Preparation for Milestones (PM Review, Online Demo) AWS Deployment Create Test Cases (Bootstrap, Top K Companions, Top K Next Places) Testing (Unit, System Integration, Regression)
Chart: 
| Programming | Non-Programming
Work Breakdown | 71 | 105

## Slide 19: Member: Samantha
Programming (67 Hours) | Non-Programming (113 Hours)
Bootstrap (Import, Validate, Logic) Login Page AGD Heatmap Debugging | Review system design Review technical documents Create Test Case (Bootstrap) Preparation for Milestones (PM Review, Online Demo) AWS Deployment Testing (Unit, System Integration, Regression)
Chart: 
| Programming | Non-Programming
Work Breakdown | 67 | 105

## Slide 20: 4. TASK AND BUG METRICS
Squish Squash Squeeze

## Slide 21: Task Metrics
Chart: Task Metrics
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Task Metric | 1.2 | 1.2 | 0.90909 | 0.69697 | 0.92 | 1.0952 | 1
For Iterations 1 & 2, there was gross over estimation of effort.
From this, we knew we were over allocating needed time for technical documents. Hence, in future iterations, we reduced the number of time allocated for creating technical documents.
# | No. of Planned tasks | No. of Actual Tasks | Score(%)
1 | 5 | 6 | 120
2 | 5 | 6 | 120
3 | 22 | 20 | 91
4 | 33 | 23 | 69. 7
5 | 50 | 46 | 92
6 | 21 | 23 | 109
7 | 16 | 16 | 1

## Slide 22: Task Metrics
Chart: Task Metrics
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Task Metric | 1.2 | 1.2 | 0.90909 | 0.69697 | 0.92 | 1.0952 | 1
For Iteration 4, there was gross under estimation of effort.
We were complacent and underestimated the difficulty of AGD and BLR because we thought we could allocate the same time we did for login and bootstrap. Codes were then not completed on time and a lot of incomplete tasks. Hence in future iterations, we discussed the major parts of the business logic during our project kickstart and from that, we were able to better derive the estimated time taken. Furthermore, we decided to allot longer sessions for AGD and BLR as well as more sessions for the two.
# | No. of Planned tasks | No. of Actual Tasks | Score(%)
1 | 5 | 6 | 120
2 | 5 | 6 | 120
3 | 22 | 20 | 91
4 | 33 | 23 | 69. 7
5 | 50 | 46 | 92
6 | 21 | 23 | 109
7 | 16 | 16 | 1

## Slide 23: Task Metrics
Chart: Task Metrics
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Task Metric | 1.2 | 1.2 | 0.90909 | 0.69697 | 0.92 | 1.0952 | 1
For Iterations 3,5,6 & 7, our estimates are fairly accurate and we are roughly on track. This goes to show that our analysis of prior iterations and discussing how we will tackle the logic of each feature at the start of each iteration paid off and that we are more in control now.
# | No. of Planned tasks | No. of Actual Tasks | Score(%)
1 | 5 | 6 | 120
2 | 5 | 6 | 120
3 | 22 | 20 | 91
4 | 33 | 23 | 69. 7
5 | 50 | 46 | 92
6 | 21 | 23 | 109
7 | 16 | 16 | 1

## Slide 24: Task Metrics
# | No. of Planned tasks | No. of Actual Tasks | Score(%)
1 | 5 | 6 | 120
2 | 5 | 6 | 120
3 | 22 | 20 | 91
4 | 33 | 23 | 69. 7
5 | 50 | 46 | 92
6 | 21 | 23 | 109
7 | 16 | 16 | 1
Follow Up Actions for Most Severe Cases:
The most severe case for our team would be that of Iteration 4. Iteration 4
was the iteration where we began tackling the complicated business logic of the project. As our group kept a close eye on the Project Schedule, we saw signs of trouble when we couldn’t think of the logic for the Auto Group Detection despite our best efforts.
Halfway through the week, we decided to inform the Project Manager about this and requested to work on Heatmap instead. Thus, we added in unplanned tasks so that we could focus on working on the slightly less complicated Heatmap instead of the Auto Group Detection which was proving to be very troublesome.
Challenges Faced:
The format of the Project Schedule was not the most intuitive of tools to be used. Therefore, we took time during the initial phases of the project to take ownership of the Project Schedule by adjusting things that we could adjust.
This included adding thick black lines to demarcate boundaries between each iteration as well as changing the datetime to DD-MMM HH:mm
[4-Sep 13:00] which was much easier to read and also reduces the likelihood of us jumbling up the date and the month.

## Slide 25: Bug Metrics
Chart: Bug Metrics
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Task Metric | 0 | 0 | 21 | 34 | 63 | 61 | 0
# | Score
1 | 0
2 | 0
3 | 21
4 | 34
5 | 63
6 | 61
7 | 0
For Iterations 1 & 2, there were no bugs due to these 2 iterations being mainly creating of technical documents and programming was done in silos without nothing substantial to test. Therefore the Scores were 0 and there was nothing to be done.
For Iteration 7, we resolved all bugs that were identified. This being the last iteration of the project, there was nothing to be done.

## Slide 26: Bug Metrics
Chart: Bug Metrics
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Task Metric | 0 | 0 | 21 | 34 | 63 | 61 | 0
# | Score
1 | 0
2 | 0
3 | 21
4 | 34
5 | 63
6 | 61
7 | 0
For Iterations 3,4,5,6 & 7 there were far more bugs being found. This resulted in us using our scheduled buffer time to take care of them. However for those which overflowed, the subsequent Project Manager planned for a debugging session to take care of these bugs before planning other more tasks.
The goal here was to take care of the critical bugs before carrying on to other parts of the project. We made use of the Bug Severity score to prioritize which bugs to take care of first which made it easier to move on from there.

## Slide 27: Bug Metrics
# | Score
1 | 0
2 | 0
3 | 21
4 | 34
5 | 63
6 | 61
7 | 0
Follow Up Actions for Most Severe Cases:
The most severe cases for our team would be that of Iteration 5 and 6. This is due to the bulk of the complex codes being implemented during these 2 iterations which resulted in more cleverly hidden bugs.
Having monitored the bug log closely and seeing the number of bugs piled up and the number of debugging sessions decreasing. We quickly informed the Project Manager and requested for even more debugging sessions in the following iterations after having exhausted the buffer we had.
Challenges Faced:
As beginners to the whole Software Engineering process, almost every member of the team were not used to the whole process of logging bugs. For those who do log it down properly, most of it were in different formats and decipherable only by its creator.
Therefore, we had to hold a meeting to bring this up and standardize a couple of things before we could move on. This saved a lot of trouble in the later parts of the project where we had to come up with the bug metrics.

## Slide 28: 5. USE OF GIT
In case of fire:
Git Commit
Git Push
Leave Building

## Slide 29: Pull Commit Push
Author | Commits
Xinyi | 41
Rainean | 43
Amos | 48
Yigang | 43
Samantha | 45
Chart: 
| Xinyi | Rainean | Amos | Yigang | Samantha
Commits | 41 | 43 | 48 | 43 | 45

## Slide 30: Team XRAYS Git 101
Copy latest Commit ID and paste
on Project Schedule
Write good commit message
Commit regularly
Test before you commit
Step 1
Step 2
Step 3
Step 4
Step 5
Ensure that work is completed before committing

## Slide 31: 6. TEST SCORE
42: The answer to life

## Slide 32: Our Results
Manual UAT Testing
JSON Automated UAT Testing
24/24
22/22

## Slide 33: 6. SERVER INFO
Bitnami

## Slide 34: SLOCA App
IP Address | http://52.221.242.151
Web URL | http://52.221.242.151/app/login.jsp
Username | admin
Password | pxraysw
Site Details
Login Credentials

## Slide 35: 7. OTHERS
Any other business

## Slide 36: Main Takeaways
If you want to go fast, go alone.
If you want to go far, go together.
Communication
A concept that is always brought up but easily forgotten. Communication is key to any successful relationship and our team has learnt the importance of saying what is on our mind; in a polite way of course. This has allowed us to trust each and made our teamwork stronger.
Assumptions
In a project with many uncertainty, the path of least resistance will be to assume and think about it later. However, this strategy has cost us dearly and taught us to never assume. Always double check.

## Slide 37: Conflict Management
Peace is not absence of conflict, it is the ability to handle conflicts by peaceful means ~ Ronald Reagan
Listening
Conflicts are necessary in order to produce innovative solutions. We have learnt to first listen before providing an objective response. Being open minded and willing to listen to others opinions and consider the fact that you may be wrong has allowed us to spend on time on quality work rather than senseless argument
Swear Jar
Having a swear jar in placed has made the environment a much more candid one. Albeit annoying at times, the jar has helped to further bond the team together. It is rather amusing that more attention is paid to the Swear jar rather than the Bug logs

## Slide 38: Something Interesting
Profanities
One of our dear members has contributed up to $20 to the Swear jar. Yet one member has yet to swear/come late during this project. Surely someone is gaining from this exchange.
The number of people in your house
It is unthinkable that you will not know the number of people in your house. However that doesn’t seem to be the case for one of our foreign friends. Either it is a trend not to know or he really doesn’t care.
Red
Also a colour found in our food establishment of choice, Tea Party is the ideal energy booster Team XRAYS partakes in almost religiously.

## Slide 39: Thank you very much for your time
If you have any questions about this document please don’t hesitate to contact us at:
EvaLive :D
Images referenced from Freepik.com