## Slide 1: XRAYS Online Demo G7T9

## Slide 2: Agenda
Timeline Overview
Functionalities
Schedule
Iteration Analysis
Metrics
Roles & Responsibilities
Pair Programming Rotation Plan

## Slide 3
Technical Documents
Project Requirements Discussion
Login
Bootstrap
Bootstrap
Basic Location Report
Bootstrap
Basic Location Report
Heatmap
Basic Location Report
Heatmap
Auto Group Detection
Auto Group Detection
Debugging
Buffer
UAT Preparation
Final Presentation Preparation
Final Presentation
Preparation
3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1. Timeline Overview

## Slide 4
Implemented Functionalities | Login & Logout Bootstrap & Additional Data Upload Basic Location Report - Top K Popular Places Heatmap
Functionalities In Progress | Basic Location Report – Breakdown Basic Location Report – Top K Companions Basic Location Report – Top K Next Place
Add On Functionalities | Dashboard (Allow user to truncate each single database table)
2. Functionalities

## Slide 5
# | Week | Tasks | Milestones | PM
1 | 3 – 4 | Documentation |  | Yigang
2 | 5 | Login & Bootstrap |  | Xinyi
3 | 6 – 7 | Bootstrap & Basic Location Report | PM Review (4 Oct) | Rainean
4 | 8 | Basic Location Report & Heatmap |  | Yigang
5 | 9 – 10 | Basic Location Report, Heatmap & Auto Group Detection | In-Class Demo (26 Oct) | Samantha
6 | 11 – 12 | Auto Group Detection, Deployment, Buffer, UAT Prep & Final Presentation Preparation | UAT (5 Nov) | Xinyi
7 | 13 – 14 | Final Presentation Preparation | Final Presentation (23 Nov) | Amos
3. Schedule

## Slide 7: 4. Iteration Analysis

## Slide 8: Iteration 3
Login & Logout
Implementation
(Day 3 to Day 7)
Bootstrap Implementation
(Day 3 to Day 9)
Integration, Testing
and Deploy (Day 11)
(Day 8 ~ 9)
Slack
Design
Review
(Day 1 and 2)
Implement BLR (Day 12)

## Slide 9
Iteration 4
Complete Auto Group Detection
(Day 2 to Day 4)
Complete BLR, Top K next place and Top K companions
(Day 2 to Day 5)
Integration, Testing
and Deploy (Day 6 ~ 7)
(Day 5)
Slack
Bootstrap (Add Files) and
Review of Tech Docs
(Day 1)

## Slide 10: Iteration 5
BLR Breakdown and
Top K Popular Places
(Day 2 to Day 6)
Heatmap
(Day 2 to Day 6)
Integration, Testing
and Deploy (Day 7)
Design
(Day 1)
Automatic Group
Detection (Day 12 to Day 13)
In-Class Demo
Preparation (Day 8
to 11)

## Slide 11: Iteration 6
Automatic Group Detection
(Day 2 to Day 3)
Debugging
(Day 2 to Day 3)
Integration, Testing
and Deploy (Day 4)
Meeting
(Day 1)
UAT Preparation (Day 8 to Day 11)
Buffer (Day 5
to Day 7)
Final Presentation
Preparation (Day 12
to Day 14)

## Slide 12: Iteration 7
Final Presentation Preparation
(Day 2 to Day 10)
Meeting
(Day 1)
Final Presentation (Day 11)

## Slide 13
5. Task Metrics
Iteration No. | Planned Tasks | Completed Tasks | Score(%) | Reflection | Action
3 | 22 | 20 | 90.0 | Basic Location Report(Top K Next Places) was pushed to the next iteration, as we under estimated for iteration 3. | We will maintain the number of pp sessions as we were on track.
4 | 33 | 23 | 69.6 | During recess week, we decided to work on heatmap instead of AGD because: 1) we got stuck at AGD logic 2) we wanted to use heatmap as our functionality for in class demo Hence the low completed task score. We reflected upon it and have made changes to iteration 5 and 6 accordingly. | We added more BLR and AGD pp sessions in future iterations. Hence we took 3 days off our initial buffer days.
5 | 53 | 22 as of now | - | Currently going well and as planned. We have managed to salvage for the under estimation from iteration 4. | -

## Slide 14
5. Bug Metrics
Iteration No. | Score | Action
3 | 21 | Prioritize bugs to be fixed during next PP session.
4 | 34 | Bugs found at the end of current iteration. Since the score only reached more than 10 on the last day of the iteration, we couldn't adjust the current iteration anymore. Thus, we added debugging sessions in the next iteration.
5 | 21 (as of now) | PM reschedules project with debugging sessions as priority before continuing with the current iteration.

## Slide 15
5. Bug Metrics (Iteration 3)
Feature | Bug Feature | Bug Severity (Score) | Found By | Date Found
Log In | Typo for retrieveUsernameFromEmail() method | Low (1) | Yigang | 1st Oct
 | Unable to login even with correct username and password | High (5) | Yigang | 
 | Admin gets stuck at a blank authenticate.jsp | Critical (10) | Samantha | 
Bootstrap | Unable to create folder when deployed to AWS | High (5) | Amos | 6th Oct

## Slide 16
5. Bug Metrics (Iteration 4)
Feature | Bug Feature | Bug Severity (Score) | Found By | Date Found
Auto Group Detection, Top K Companions, Top K Next Places | Dropdown for user logout not working | Low (1) x 3 | Rainean | 14th Oct
Top K Companions and Top K Next Places | Submit button missing | High (5) x 2 | Rainean | 15th Oct
Top K Companions and Next Places | Gets stuck at the controller page | Critical (10) x 2 | Yigang | 15th Oct
Top K Next Places | Does not show ties in rank | Low (1) | Xinyi | 15th Oct

## Slide 17
5. Bug Metrics (Iteration 5)
Feature | Bug Feature | Bug Severity (Score) | Found By | Date Found
Top K Popular Place | Input time of 12:00:00 gets converted into 00:00:00 | High (5) | Amos | 19th Oct
Top K Popular Place | If input date time does not have data, page gets stuck at controller | Critical (10) | Yigang | 19th Oct
Heatmap | Considers location updates outside the 15 min query window | High (5) | Samantha | 19th Oct
Heatmap | Results don’t show density 0 | Low (1) | Samantha | 19th Oct

## Slide 18
6. Roles & Responsibilities
          Who did what?
Member | Programming | Non-Programming
Xinyi | Bootstrap (Import & Validation) Basic Location Reports (Breakdown, Top K Companions, Top K Next Places, Top K Popular Place) System Integration Debugging | Initial discussion for project Initial documents creation Review system design Review technical documents Preparation for Milestones (PM Review, Online Demo) Testing (Unit, System Integration, Regression) AWS Deployment

## Slide 19
6. Roles & Responsibilities
          Who did what?
Member | Programming | Non-Programming
Rainean | Login Page Bootstrap (Import) Basic Location Reports (Breakdown, Top K Companions, Top K Next Places, Top K Popular Place) Integration (Top K Companions, Top K Next Places, AGD) Debugging | Initial discussion for project Initial documents creation Review system design Review technical documents Preparation for Milestones (PM Review, Online Demo) Testing (Unit, System Integration) AWS Deployment

## Slide 20
6. Roles & Responsibilities
          Who did what?
Member | Programming | Non-Programming
Amos | Bootstrap (Import, Validate, Logic) Login Page Basic Location Reports (Breakdown, Top K Popular Place) AGD Heatmap Debugging | Initial discussion for project Initial documents creation Review system design Review technical documents Preparation for Milestones (PM Review, Online Demo) System Integration & Regression Testing AWS Deployment Testing (Unit, System Integration)

## Slide 21
6. Roles & Responsibilities
          Who did what?
Member | Programming | Non-Programming
Yigang | Login Page Bootstrap (Import, Validate) Basic Location Reports (Top K Next Places, Breakdown, Top K Popular Place) Debugging | Initial discussion for project Initial documents creation Review system design Review technical documents Preparation for Milestones (PM Review, Online Demo) AWS Deployment Create Test Cases (Bootstrap, Top K Companions, Top K Next Places) Testing (Unit, System Integration, Regression)

## Slide 22
6. Roles & Responsibilities
          Who did what?
Member | Programming | Non-Programming
Samantha | Bootstrap (Import, Validate, Logic) Login Page AGD Heatmap Debugging | Initial discussion for project Initial documents creation Review system design Review technical documents Create Test Case (Bootstrap) Preparation for Milestones (PM Review, Online Demo) AWS Deployment Testing (Unit, System Integration, Regression)

## Slide 23
7. Pair Programming Rotation Plan
Week | PM | Pair 1 | Pair 2
Week 3 - Week 4 | Yigang | Amos & Rainean | Samantha & Xinyi
Week 5 | Xinyi | Rainean & Yigang | Amos & Samantha
Week 6- Week 7 | Rainean | Amos & Xinyi | Samantha & Yigang
Week 8 | Yigang | Rainean & Xinyi | Amos & Samantha
Week 9 - Week 10 | Samantha | Amos & Rainean | Xinyi & Yigang
Week 11 - Week 12 | Xinyi | Amos & Yigang | Rainean & Samantha
Week 13 - Week 14 | Amos | Samantha & Xinyi | Rainean & Yigang