## Slide 1
X R A Y S
PM REVIEW
G7T9

## Slide 2: Content Page
Timeline Overview
Functionalities
Schedule
Iteration Analysis
Metrics
Roles & Responsibilities
Pair Programming Rotation Plan
Q&A

## Slide 3: Timeline Overview
Technical Documents & Project Requirements
Discussion
Login & Bootstrap
Bootstrap & Basic Location Report
Bootstrap
Basic Location Report
Auto Group Detection
Basic Location Report &
Heatmap
Buffer
UAT Preparation
Final Presentation
Preparation
3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## Slide 4
Functionalities
Tentative Additional Functions | User Account Controls (Password Reset, Change Password) Password Hashing
Framework | No Framework Used Following MVC Design Pattern
Implemented Functions | Login/Logout Bootstrap (Demographics/Location-Lookup/Location)

## Slide 5
Schedule
# | Week | Functions | Milestones | PM
1 | 3 – 4 | Documentation |  | Yigang
2 | 5 | Login & Bootstrap |  | Xinyi
3 | 6 – 7 | Bootstrap & Basic Location Report | PM Review (4 Oct) | Rainean
4 | 8 | Basic Location Report & Auto Group Detection |  | Yigang
5 | 9 – 10 | Basic Location Report & Heatmap | In-Class Demo (26 Oct) | Samantha
6 | 11 – 12 | Buffer & UAT Prep | UAT (5 Nov) | Xinyi
7 | 13 – 14 | Final Presentation Preparation | Final Presentation (23 Nov) | Amos

## Slide 6: Iteration Analysis

## Slide 7
7
Iteration 1 (2 Weeks)
Login
(Day 14)
Discussion
(Day 1 and 2)
Class, Use Case, Sequence and Logical Diagram
(Day 3 to Day 13)

## Slide 8: Iteration 1 Analysis
Main Focus:
Project Wiki Discussion
Creating of Technical Documents
PM: Yigang
Samantha & Xinyi
Rainean & Amos
Add On:
Refresher of Java
JSP Introduction

## Slide 9
9
Iteration 2 (1 Week)
Login Page Implementation
(Day 2 to Day 4)
Bootstrap Implementation
(Day 2 to Day 4)
System Testing (Day 4)
Tech
Documents
(Day 1)

## Slide 10: Iteration 2 Analysis
Main Focus:
Complete Login Page
Bootstrap (Upload Demographics.csv)
PM: Xinyi
Amos & Samantha (Bootstrap)
Rainean & Yigang (Login)
Pitfall:
Login added as a task in the next iteration due to task underestimation

## Slide 11
11
Iteration 3 (2 Weeks)
Login & Logout
Implementation
(Day 3 to Day 7)
Bootstrap Implementation
(Day 3 to Day 9)
Integration, Testing
and Deploy (Day 11)
(Day 8 ~ 9)
Slack
Design
Review
(Day 1 and 2)
Implement BLR (Day 12)

## Slide 12: Iteration 3 Analysis
Main Focus:
Complete Login & Continue Bootstrap
PM: Rainean
Amos & Xinyi (Bootstrap)
Yigang & Samantha (Login, Bootstrap assist)
Pitfall:
Bootstrap (Additional Data) will not be completed by this iteration
Milestone: PM Review

## Slide 13
13
Iteration 4 (1 Week)
Complete Auto Group Detection
(Day 2 to Day 4)
Complete BLR, Top K next place and Top K companions
(Day 2 to Day 5)
Integration, Testing
and Deploy (Day 6 ~ 7)
(Day 5)
Slack
Bootstrap (Add Files) and
Review of Tech Docs
(Day 1)

## Slide 14: Iteration 4 Analysis
Main Focus:
Complete Bootstrap
Top K Companions, Top K Next Places Auto Group Detection
PM: Yigang
Rainean & Xinyi (Top K)
Amos & Samantha (Bootstrap, AGD, Top K Assist)
Pitfall:
Basic Location Report will not be completed by Iteration 4

## Slide 15
15
Iteration 5 (2 Weeks)
BLR Breakdown and
Top K Popular Places
(Day 2 to Day 6)
Heatmap
(Day 2 to Day 6)
Integration, Testing
and Deploy (Day 6 to Day 10)
Design
(Day 1 and 2)
Heatmap (Day 12 to Day 13)

## Slide 16: Iteration 5 Analysis
Main Focus:
BLR & Heatmap
PM: Samantha
Amos & Rainean (Heatmap)
Yigang & Xinyi (BLR, Heatmap Assist)
Add On:
Heatmap displayed in graphical format
Milestone: In Class Demo

## Slide 17
17
Iteration 6 (2 Weeks)
Buffer
(Day 2 to Day 7)
UAT Prep (Day 8 to Day 10)
Meeting
(Day 1)

## Slide 18: Iteration 6 Analysis
Main Focus:
Buffer and finalize project
PM: Xinyi
Amos & Yigang
Rainean & Samantha
Pitfall: Insufficient Buffer Time
Add On: Implement additional functions that were considered
Milestone: UAT

## Slide 19
19
Iteration 7 (2 Weeks)
Final Presentation Preparation
(Day 2 to Day 10)
Final Presentation
(Day 11)
Meeting
(Day 1)

## Slide 20: Iteration 7 Analysis
Main Focus:
Final Presentation Preparation
PM: Amos
Xinyi & Samantha
Rainean & Yigang
Milestone: Final Presentation

## Slide 21: Metrics

## Slide 22
Task Metric

## Slide 23
Task Metric
Iteration | Score (%) | Action
1 | 120 | Gross Over Estimation of Effort Technical documents took shorter than expected. We will plan for shorter duration for technical documents in the future which will provide us more time for other tasks.
2 | 80 | Gross Under Estimation of Effort Programming duration took longer than expected. We will take into account the pair programmers’ abilities and plan for longer PP sessions which will provide us with a more realistic view of our timeline.
3 | - | 

## Slide 24
Task Metric
Iteration | Planned Tasks | Completed Tasks
1 | 5 | 6
2 | 5 | 4
3 | 22 | 16 as of now

## Slide 25
Bug Metric

## Slide 26
Bug Metric

## Slide 27
Bug Metric
Iteration | Score | Action
1 | 0 | None. Continue with development
2 | 0 | None. Continue with development
3 | 16 | Prioritize bugs to be fixed during next PP session.

## Slide 28
Bug Metric (Iteration 3)
Feature | Bug Feature |  | Bug Severity | Found By | Date Found
Login | Typo for retrieveUsernameFromEmail() method |  | Low (1) | Yigang | 1st Oct
 | Unable to login with correct username and password |  | High (5) | Yigang | 
 | Admin gets stuck at a blank authenticate.jsp |  | Critical (10) | Samantha | 
Bootstrap | AWS bootstrap shows filepath not found error |  |  |  | 5th Oct

## Slide 29: Project Planning

## Slide 30: Roles & Responsibilities
Project Manager | Pair Programmers
Complete minutes Ensure documents are pushed to git | Code during scheduled pair programming sessions
Proper takeover from previous PM, proper hand over to next PM | Every PP session: Pull at the start, commit during, push at the end
Keep updated with the progress of pair programmers | Inform PM before pushing codes
Ensure the team is on track and detailed schedule is up to date, adjust accordingly | Upload PP picture, submit commit ID on detailed schedule

## Slide 31: PM to Milestone Matching
Milestone | PM
PM Review | Rainean
In-Class Demo | Samantha
UAT | Xinyi
Final Presentation | Amos

## Slide 32: Pair Programming – Rotation Plan
Week | PM | Pair 1 | Pair 2
Week 3 - Week 4 | Yigang | Amos & Rainean | Samantha & Xinyi
Week 5 | Xinyi | Rainean & Yigang | Amos & Samantha
Week 6- Week 7 | Rainean | Amos & Xinyi | Samantha & Yigang
Week 8 | Yigang | Rainean & Xinyi | Amos & Samantha
Week 9 - Week 10 | Samantha | Amos & Rainean | Xinyi & Yigang
Week 11 - Week 12 | Xinyi | Amos & Yigang | Rainean & Samantha
Week 13 - Week 14 | Amos | Samantha & Xinyi | Rainean & Yigang

## Slide 33
Q & A